## Tasks
ID | Project | Task Name | Task Brief | Department | Internal POC | Agency | Vendor | Priority | Task Progress | Deadline | Execution Started | Execution Start Date | Actual Finished Date | To Be Approved By Management | Submitted For Approval At | Approval Date | Rejection Reason | Remarks | Budget | Actual Spend | Subtasks | Comments | Is Overdue | Created At | Updated At | Deleted At
TSK-1001 | Q3 Brand Awareness Campaign | Hero Billboard Video Commercial Production | Create a 30-second high-impact anamorphic 3D video commercial for Times Square and digital displays. | Brand & Creative | Ananya Gupta | Apex Creative Studio | PixelPerfect Visuals | Urgent | In Progress | 2026-08-10 | TRUE | 2026-07-15 |  | FALSE |  |  |  | Script approved by CMO. Initial 3D renders in review. | 25000 | 18500 | [{"id":"st-1","title":"Scriptwriting & Storyboard Sign-off","completed":true},{"id":"st-2","title":"3D Anamorphic Model Render","completed":true},{"id":"st-3","title":"Sound Design & Voiceover Audio","completed":false},{"id":"st-4","title":"Final 4K Resolution Export","completed":false}] | [{"id":"c-1","author":"Ananya Gupta","role":"Marketing Team","text":"Initial 3D render draft sent to CMO for feedback.","timestamp":"2026-07-28T14:20:00Z"},{"id":"c-2","author":"Management Approver","role":"Management","text":"Looks promising! Please boost contrast on product logo in frame 4.","timestamp":"2026-07-28T16:00:00Z"}] | FALSE | 2026-07-15T09:30:00Z | 2026-07-28T14:20:00Z
TSK-1002 | Product Launch v4.0 | GTM Keynote Deck & Launch Video Package | Design executive presentation slides and produce CEO keynote opening teaser video. | Product Marketing | Priya Verma | Apex Creative Studio | OmniStream Video | High | To Be Approved by Management | 2026-08-05 | TRUE | 2026-07-10 |  | TRUE | 2026-07-28T09:15:00.000Z |  |  | Awaiting final sign-off from Management before publishing collateral. | 15000 | 14200 | [{"id":"st-201","title":"Executive Outline & Speaker Notes","completed":true},{"id":"st-202","title":"Custom 4K Motion Slides","completed":true},{"id":"st-203","title":"Teaser Video Sound Sync","completed":true}] | [{"id":"c-201","author":"Priya Verma","role":"Marketing Team","text":"Submitted package for final Management approval.","timestamp":"2026-07-29T10:15:00Z"}] | FALSE | 2026-07-10T11:00:00Z | 2026-07-29T10:15:00Z
TSK-1003 | SEO & Content Overhaul | Q3 Pillar Blog Posts & Whitepaper Design | Write 5 technical pillar guides and design downloadable PDF eBooks for lead generation. | Content & PR | Rohan Mehta | Echo PR Studio | PrintCraft Solutions | Medium | In Progress | 2026-08-15 | TRUE | 2026-07-18 |  | FALSE |  |  |  | 3 out of 5 articles drafted. PDF layout template ready. | 8000 | 4500 | [{"id":"st-301","title":"Pillar Articles 1-3 Writing","completed":true},{"id":"st-302","title":"Pillar Articles 4-5 Writing","completed":false},{"id":"st-303","title":"PDF Layout Design","completed":true}] | [] | FALSE | 2026-07-18T08:00:00Z | 2026-07-27T16:45:00Z
TSK-1004 | Annual Customer Conference 2026 | Sponsor Booth Signage & Swag Production | Print custom fabric backdrops, acrylic signs, and eco-friendly swag boxes for attendees. | Event Marketing | Karan Patel | Apex Creative Studio | PrintCraft Solutions | Urgent | Overdue | 2026-07-25 | TRUE | 2026-07-02 |  | FALSE |  |  |  | Vendor shipment delayed by 3 days. Urgently tracking delivery. | 30000 | 31500 | [{"id":"st-401","title":"Vector Artwork Final Approval","completed":true},{"id":"st-402","title":"Fabric Banner Printing","completed":true},{"id":"st-403","title":"Eco Swag Box Assembly & Shipping","completed":false}] | [] | TRUE | 2026-07-02T10:00:00Z | 2026-07-26T09:00:00Z
TSK-1005 | Social Media Growth Hacking | July Reel & TikTok Series (20 Videos) | Film and edit 20 short-form educational videos highlighting product features. | Brand & Creative | Aarav Sharma | Apex Media Global | PixelPerfect Visuals | Medium | Completed | 2026-07-28 | TRUE | 2026-07-01 | 2026-07-27 | FALSE |  | 2026-07-27 |  | All 20 videos scheduled on Buffer. Average engagement up 40%. | 12000 | 11000 | [{"id":"st-501","title":"Video Concepts & Captions","completed":true},{"id":"st-502","title":"Shooting Day 1 & 2","completed":true},{"id":"st-503","title":"Color Grading & Subtitle Editing","completed":true}] | [] | FALSE | 2026-07-01T14:00:00Z | 2026-07-27T18:00:00Z
TSK-1006 | Q3 Brand Awareness Campaign | Meta & LinkedIn Paid Ads Setup | Configure ad accounts, pixel tracking, audience retargeting, and creative variations. | Performance Marketing | Priya Verma | Apex Media Global | CloudScale Hosting | High | To Be Approved by Management | 2026-08-02 | TRUE | 2026-07-20 |  | TRUE | 2026-07-28T09:15:00.000Z |  |  | Ad copy and $50k budget allocation pending Management approval. | 50000 | 50000 | [] | [] | FALSE | 2026-07-20T13:00:00Z | 2026-07-29T11:30:00Z
TSK-1007 | Product Launch v4.0 | Customer Case Study Video Series | Interview 3 enterprise customers and edit 3-minute success story videos. | Product Marketing | Rohan Mehta | Echo PR Studio | OmniStream Video | Low | Not Started | 2026-08-25 | FALSE |  |  | FALSE |  |  |  | Customer consent forms sent out. | 18000 | 0 | [] | [] | FALSE | 2026-07-22T15:00:00Z | 2026-07-22T15:00:00Z

## Projects
ID | Name | Status | Description | Created At | Updated At | Deleted At
proj-1 | Q3 Brand Awareness Campaign | Active | National digital and out-of-home campaign | 2026-07-01 | 2026-07-01
proj-2 | Product Launch v4.0 | Active | GTM strategy & creative collateral | 2026-07-05 | 2026-07-05
proj-3 | SEO & Content Overhaul | Active | Blog and landing page optimization | 2026-07-10 | 2026-07-10
proj-4 | Annual Customer Conference 2026 | Active | Event marketing & sponsor booth designs | 2026-07-12 | 2026-07-12
proj-5 | Social Media Growth Hacking | Active | Short-form video and influencer partnerships | 2026-07-15 | 2026-07-15

## Vendors
ID | Name | Status | Description | Created At | Updated At | Deleted At
vendor-1 | PrintCraft Solutions | Active | Large format printing and merchandise | 2026-07-01 | 2026-07-01
vendor-2 | CloudScale Hosting | Active | CDN and landing page infrastructure | 2026-07-01 | 2026-07-01
vendor-3 | OmniStream Video | Active | Livestreaming equipment rental | 2026-07-01 | 2026-07-01
vendor-4 | EventPro Logistics | Active | Booth shipping & booth construction | 2026-07-01 | 2026-07-01

## Agencies
ID | Name | Status | Description | Created At | Updated At | Deleted At
agency-1 | Apex Creative Studio | Active | Full-service digital creative agency | 2026-07-01 | 2026-07-01
agency-2 | Apex Media Global | Active | Performance media buying partner | 2026-07-01 | 2026-07-01
agency-3 | Echo PR Studio | Active | Public relations and communications | 2026-07-01 | 2026-07-01
agency-4 | PixelPerfect Visuals | Active | Video production & 3D motion graphics | 2026-07-01 | 2026-07-01

## Departments
ID | Name | Status | Description | Created At | Updated At | Deleted At
dept-1 | Brand & Creative | Active | Design, video, branding assets | 2026-07-01 | 2026-07-01
dept-2 | Performance Marketing | Active | PPC, Meta Ads, Paid Search | 2026-07-01 | 2026-07-01
dept-3 | Product Marketing | Active | Sales enablement, positioning, collateral | 2026-07-01 | 2026-07-01
dept-4 | Content & PR | Active | Blog posts, press releases, copy | 2026-07-01 | 2026-07-01
dept-5 | Event Marketing | Active | Field events, webinars, conferences | 2026-07-01 | 2026-07-01

## Team Members
ID | Name | Status | Description | Created At | Updated At | Deleted At
team-1 | Aarav Sharma | Active | Lead Creative Strategist | 2026-07-01 | 2026-07-01
team-2 | Priya Verma | Active | Senior Growth Marketer | 2026-07-01 | 2026-07-01
team-3 | Rohan Mehta | Active | Content Marketing Manager | 2026-07-01 | 2026-07-01
team-4 | Ananya Gupta | Active | Design Director | 2026-07-01 | 2026-07-01
team-5 | Karan Patel | Active | Events Coordinator | 2026-07-01 | 2026-07-01

## Activity Log
ID | User | Role | Date | Time | Action | Target | Old Value | New Value
log-1 | Management Admin | Admin | 2026-07-29 | 11:30:12 | Approval Requested | TSK-1006 | In Progress | To Be Approved by Management
log-2 | Priya Verma | Marketing Team | 2026-07-29 | 10:15:44 | Status Updated | TSK-1002 | In Progress | To Be Approved by Management
log-3 | Aarav Sharma | Marketing Team | 2026-07-27 | 18:00:00 | Task Completed | TSK-1005 | In Progress | Completed
log-4 | System Automation | Admin | 2026-07-26 | 00:01:00 | Overdue Triggered | TSK-1004 | In Progress | Overdue

## Users
Email | Name | Role | Status | Last Login At | Created At | Updated At | Deleted At
admin@marketingdashboard.com | System Admin | Admin | Active | 2026-07-29T12:00:00Z | 2026-07-01T00:00:00Z | 2026-07-01T00:00:00Z

## Settings
Key | Value | Description
APP_TIMEZONE | Asia/Kolkata | Default business timezone for task deadlines and completion tracking
APP_NAME | Marketing Task Dashboard | Workspace Display Name

## Reports
Metric | Value | Generated At

## Dashboard
KPI | Value | Generated At